## Start
5S Implementation Kit
Rollout, audit and sustaining the standard. An Excel tool (no macros).
Company: | Enter the company or client name
Version 1.0 | Process Lab Pro ¦ processlabpro.com
How to start: 6 steps
1. Settings | Enter the company name, areas and auditors (yellow fields). The target defaults to 80%.
2. 90-day rollout | Assign owners and dates. Progress calculates itself.
3. Red tags | During the 1S campaign, register the tagged items. Decision within 7 days.
4. Scores | Each column is one audit: date, area, auditor and 40 scores (0–4 or NA).
5. Action plan | Turn every audit finding into an action with an owner and a deadline.
6. Dashboard | Choose an area and watch the trend, 5S profile, ranking and overdue actions.
Table of tabs (click to jump)
Settings | Company, areas, auditors, target and thresholds
Checklist | 40 questions with a description of what to check and what an exemplary score looks like
Scores | Score sheet: up to 60 audits, 1S–5S scores calculated automatically
Dashboard | Score, change, 5S radar, trend, area ranking
Action plan | Action register with deadlines and overdue statistics
Red tags | Register of items tagged during sorting
Audit schedule | Annual plan versus completion (from the Scores tab)
90-day rollout | Task list for 30/60/90 days with progress
Calculations | Helper, do not edit
Legend
Input field | Yellow background, blue font: you enter your own data.
Calculated field | White background: formula result. Do not overwrite.
Score at or above target (default 80%)
Needs improvement (default 60–79%)
Critical (below the warning threshold)
Licence and notes
Licence for internal use at one plant. Resale, sharing with third parties and publication in whole or in part without the author's consent are prohibited. The tool contains no macros, so it does not require permission to run macros. It works in Microsoft Excel 2010 and newer and in LibreOffice Calc.
© Process Lab Pro ¦ processlabpro.com

## Settings
Settings
Change the yellow fields. Area and auditor names feed the drop-down lists throughout the file.
Company / client name | Enter the company or client name
Audit plan year | 2026
Target: goal score (green) | 80%
Warning threshold (below = red) | 60%
Areas (up to 15) | Auditors (up to 10) | Action statuses | Priority | Source of report | Tag reason | Tag decision | Tag status | Task status | Criterion (S)
Production line 1 | 5S leader | Open | High | 5S audit | Unneeded | Stays (returns to its place) | Pending decision | To do | 1S Sort
Production line 2 | Auditor 2 | In progress | Medium | Daily check | Damaged | Move to another area | Decided | In progress | 2S Set in Order
Materials warehouse | Auditor 3 | Closed | Low | Management gemba | Surplus | Sell or transfer | Completed | Done | 3S Shine
Finished goods warehouse |  | Cancelled |  | Employee report | Unknown purpose | Scrap / dispose |  | Not applicable | 4S Standardize
Tool room |  |  |  | Other | Contaminated | Pending decision |  |  | 5S Sustain
Maintenance |  |  |  |  | Other
Quality control
Packing
The lists in columns E–L feed the drop-down lists. Do not rename them, because formulas look for these words (e.g. "Closed").
How the score is calculated
Question score: 0–4 points. "NA" (not applicable) excludes the question from the score.
1S–5S score = sum of points / (number of scored questions × 4).
Overall score = average of the five S scores, so each S carries the same weight.
An incomplete audit (fewer than 40 answers) is counted, but you will see it in the "Completeness" row.

## Checklist
5S audit checklist: 40 questions, 0–4 scale
You can adapt the questions to your plant (yellow fields). Changes appear immediately in the "Scores" tab. For a client version: change only the wording, not the number of questions.
Scoring scale
4 | Exemplary | Requirement fully met, sustained over time and confirmed by the team.
3 | Good | Met for the most part. Minor deviations that the team notices and corrects itself.
2 | Partially | Met roughly half-way. Visible gaps, no steady habit.
1 | Poor | Individual elements are in place, but there is no system or sustaining.
0 | None | Requirement not met or does not exist.
NA | Not applicable | The question does not apply in this area. It is not included in the score.
Nr | Criterion | Audit question | What to check | Exemplary (4 pts) | Problem signal (0–1 pts)
1.1 | 1S Sort | There are no items in the area that are unnecessary for current work (tools, materials, parts, documents). | Worktops, shelves, cabinets, floor, the space behind machines and on top of cabinets. Control question: do you use it every shift or every week? | Only what is needed on the given shift is at the workstation; everything else has a defined place outside the work zone. | Old fixtures after a model change, cartons, parts kept "just in case".
1.2 | 1S Sort | Items with no owner or unclear purpose carry a red tag with a decision deadline. | Are the tags hanging? Do they have a date and a decision owner? Does the tag register match what lies in the area? | Every item of unclear status has a tag, decisions are made within 7 days, the register is up to date. | Things lie around unmarked, or tags hang for weeks without a decision.
1.3 | 1S Sort | The quarantine zone (red zone) is designated, labelled and emptied regularly. | Location and marking of the zone, dates on tags, whether the zone has turned into a dumping ground. | The zone is clearly marked and nothing stays in it longer than the agreed deadline. | No zone, or a zone full of things from months ago.
1.4 | 1S Sort | Materials, semi-finished and finished goods are present in the necessary quantities only (per min/max). | Compare quantities in the area with the set limits; check pallets at the machine and WIP containers. | Quantities are within limits, and any excess is reported immediately. | Stock "for a few shifts ahead", unlabelled pallets, piles of semi-finished goods.
1.5 | 1S Sort | Damaged, worn or faulty tools and equipment are removed from the area or clearly marked. | Tool drawers, holders, measuring instruments, carts, ladders, guards. | No faulty tools in use; defective ones are marked and reported for repair or disposal. | Broken tools that "still work"; a cart with a damaged wheel.
1.6 | 1S Sort | Documents and instructions at the workstation are current, and outdated ones have been removed. | Versions and dates of instructions, check sheets, notes on walls and machines. | Only current versions, in one designated place, with no handwritten notes. | Yellowed sheets, several versions of the same instruction, notes stuck on with tape.
1.7 | 1S Sort | Personal and non-production items (clothing, drinks, food, phones) are only in designated places. | Worktops, machine panels, tool cabinets, bins. | There are no personal items in the production zone, and employees have lockers or a changing room. | Jackets on machines, bottles on worktops next to material.
1.8 | 1S Sort | There are no hidden stockpiles in cabinets, drawers or under tables. | Open three cabinets or drawers at random, look under tables and behind racks. | The contents of each cabinet match its description and the needs of the workstation. | Drawers full of random parts, cartons under the table.
2.1 | 2S Set in Order | Every item has a fixed, marked place (outline, tool shadow, label or location address). | Pick five items at random and ask for their place to be shown. | All checked items have an unambiguous place, and a new person finds them without asking. | Places "in employees' heads", tools in a heap.
2.2 | 2S Set in Order | Layout follows frequency of use: the most frequent within hand's reach, the rarer further away. | Watch the work for 5 minutes: how many steps, bends and searches are there. | Items used every shift are within arm's reach, and unnecessary movements are limited. | A frequently used tool lies in a distant cabinet.
2.3 | 2S Set in Order | Storage locations have a marked minimum and maximum level. | Min/max lines on racks, kanbans, shelves; do employees know them? | Min/max is marked and observed; shortages and surpluses are visible immediately. | No limits, piles beyond capacity, overfilled racks.
2.4 | 2S Set in Order | Floor marking (zones, routes, pallet positions) is legible, and fire equipment and emergency exits are accessible. | Condition of paint or tape; does anything block extinguishers, hydrants, electrical cabinets and routes? | Markings are legible and complete; all routes and safety equipment are clear. | Worn lines, a pallet standing on the line, a blocked walkway.
2.5 | 2S Set in Order | Racks, cabinets and containers are clearly labelled (labels understandable to a new person). | Labels: uniform, visible from 2–3 m, current and resistant to shop-floor conditions. | A uniform labelling system, visible from a distance, matching the contents. | Handwritten notes, peeling stickers, labels that do not match the contents.
2.6 | 2S Set in Order | A missing or misplaced item is visible at once (visual check within 30 seconds). | Ask: can you see that something is missing? Check tool shadows, outlines, colour indicators. | Deviations from the standard are visible immediately, without counting or searching. | Nobody notices the absence until the tool is needed.
2.7 | 2S Set in Order | Cables, hoses and wires are organised and neither hinder work nor create a trip hazard. | Walkways, workplaces, dangling pneumatic hoses, extension cords. | Run in trays or suspended, labelled, no tangle. | Extension cords on the floor, hoses pulled across the walkway.
2.8 | 2S Set in Order | Waste bins and sorted waste have a fixed, marked place. | Colours, labelling of fractions, accessibility, no mixing of waste. | Segregation follows plant rules, bins are labelled and in fixed locations. | Mixed waste, unlabelled bins, "wild" storage.
3.1 | 3S Shine | Floors, worktops and machines are clean (no dust, chips, oil, material residue). | Run a finger over a machine surface, look under the machine, on top of cabinets and in corners. | No visible contamination; hard-to-reach places are clean too. | A layer of dust or chips, oil stains, material residue on the floor.
3.2 | 3S Shine | The cleaning plan clearly states: what, who, how often and with what is cleaned. | Is the plan posted, current, filled in and understandable also for the night shift? | A plan with named owners and frequency is carried out and confirmed. | No plan, or "whoever notices cleans".
3.3 | 3S Shine | Cleaning tools and supplies are available on site, complete and in working order. | Brooms, dustpans, rags, absorbents, vacuum cleaner: place, completeness, condition. | The cleaning kit is in the area, has a fixed place and is in working order. | Equipment has to be fetched from the other end of the hall or is worn out.
3.4 | 3S Shine | Cleaning is combined with inspection: leaks, looseness, seepage and damage are reported. | Ask the operator what they noticed recently while cleaning; check maintenance requests. | Abnormalities go into the request register and are closed out. | A leak that "has always been there", no requests.
3.5 | 3S Shine | Sources of contamination (leaks, dust, process waste) are identified and eliminated at the source. | List of sources, guards, trays, extraction; actions recorded in the action plan. | Main sources have actions assigned, and contamination levels clearly fall. | Cleaning the same spot over and over without looking for the cause.
3.6 | 3S Shine | Lighting works and is clean; guards, windows and information boards are legible. | Lamps, displays, machine windows, sensor covers. | Full, clean lighting, transparent guards, legible information. | Burnt-out lamps, dirty windows, illegible boards.
3.7 | 3S Shine | Waste bins are not overfilled and are emptied according to schedule. | Fill level, surroundings of the bins, emptying schedule. | Bins emptied on time, never above 80% capacity. | Overflowing bins, waste next to the containers.
3.8 | 3S Shine | Oil and chemical zones are sealed and clean; spill trays and absorbents are available. | Trays, drums, refuelling points, safety data sheets, completeness of absorbents. | No leaks, dry trays, complete absorbents known to employees. | Leaks, no trays, used and unreplenished absorbent.
4.1 | 4S Standardize | The area's appearance standard (photos of the target state) is available in the area and current. | Reference photos: are they posted, do they match reality, update date. | Current standard photos are posted in a visible place and cover the key points of the area. | No standard, or the photos do not match the workstation.
4.2 | 4S Standardize | Marking rules (colours, labels, symbols) are uniform in the area and consistent with plant rules. | Compare with the neighbouring area: do colour and label mean the same thing? | One rule across the plant, described in the standard. | Every department uses different colours and labels.
4.3 | 4S Standardize | Roles and responsibilities are defined: area owner, 5S leader, people responsible for zones. | A board with names or a responsibility matrix; do employees know who is responsible for what? | Roles are assigned by name, and everyone knows them and confirms them in conversation. | "Everyone is responsible for 5S", meaning nobody is.
4.4 | 4S Standardize | Visual management works: markings, indicators and information boards are complete and legible. | Min/max indicators, level and pressure markings, boards, zones. | The state of key parameters is visible without asking and without documents. | Markings faded, incomplete or incomprehensible.
4.5 | 4S Standardize | A daily (5-minute) 5S checklist exists and is actually filled in. | Completion over the last 10 days and whether entries match the real state of the area. | The list is filled in daily by operators, and deviations have actions. | The list filled in "in bulk" before an audit, or empty.
4.6 | 4S Standardize | Standards are visual (photos, drawings, colours) and understandable without reading long instructions. | Ask a new person to recreate the standard from the document. | The standard is understood in 1–2 minutes, also by a person from another shift. | The standard is a multi-page text nobody has read.
4.7 | 4S Standardize | New employees are trained in the 5S standard of their area, and the training is documented. | Entry in the workstation training record; a conversation with the most recently hired person. | Every new person completes training in the first week and confirms it with a signature. | The standard is passed on "by word of mouth".
4.8 | 4S Standardize | Changes (new machine, layout change, new product) result in an update of the 5S standard. | Recent changes in the area and the date of the last standard update. | Updating the standard is part of the change process; the standard always matches the actual state. | The workstation was rebuilt and the standard stayed old.
5.1 | 5S Sustain | Employees keep order up to date, without reminders or inspection. | Unannounced observation: behaviour during the shift and the state of the area in the middle of it. | Order is a natural part of the work, and the team corrects deviations immediately. | Order only "for the audit".
5.2 | 5S Sustain | The daily 5 minutes at the end of the shift (cleaning and check) is carried out. | Ask the shift whether and when they do it; check the state at the start of the next shift. | A fixed end-of-shift ritual; the area is handed over to the next shift according to the standard. | The next shift starts by cleaning up after the previous one.
5.3 | 5S Sustain | Audits take place on schedule, and the results are posted in the area. | Schedule versus completion, results board, how current the last result is. | 100% of audits done on time; results visible and discussed. | Audits postponed because "there is too much work".
5.4 | 5S Sustain | Actions from previous audits are completed on time. | Action plan: number open, overdue, findings repeating from audit to audit. | At least 90% of actions closed on time, and findings do not repeat. | The same findings from audit to audit.
5.5 | 5S Sustain | Management regularly visits the area and checks 5S on site (gemba). | Visit records, conversation with employees about the manager's last visit. | Weekly presence of the manager, specific questions and decisions. | The manager sees 5S only in a presentation.
5.6 | 5S Sustain | Employees know the 5S rules and can explain what their duties are. | Ask 2–3 people: what is a red tag? What are you responsible for in 5S? | Every person asked answers correctly and specifically. | They do not know what the markings mean or why they are there.
5.7 | 5S Sustain | Employee ideas and comments about 5S are collected and considered, and authors get feedback. | Suggestion box or board, number of submissions, response time. | Submissions are regular, response within 7 days, implemented ideas are visible. | Ideas disappear without an answer.
5.8 | 5S Sustain | 5S results are trended and discussed in meetings; the score holds at the target level or rises. | Trend chart on the board, review minutes, direction of the last three results. | Score at or above target in the last three audits, trend discussed monthly. | The score falls and nobody discusses it.

## Scores
Score sheet: one column = one audit
Enter the date, choose the area and auditor, then score the points (0–4 or NA). Results are calculated automatically at the bottom and in the Dashboard tab. New audit = next free column.
Audit no. |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Audit date
Area
Auditor
Point scores (0–4 or NA)
1S | Sort (Seiri)
1.1 | There are no items in the area that are unnecessary for current work (tools, materials, parts, documents).
1.2 | Items with no owner or unclear purpose carry a red tag with a decision deadline.
1.3 | The quarantine zone (red zone) is designated, labelled and emptied regularly.
1.4 | Materials, semi-finished and finished goods are present in the necessary quantities only (per min/max).
1.5 | Damaged, worn or faulty tools and equipment are removed from the area or clearly marked.
1.6 | Documents and instructions at the workstation are current, and outdated ones have been removed.
1.7 | Personal and non-production items (clothing, drinks, food, phones) are only in designated places.
1.8 | There are no hidden stockpiles in cabinets, drawers or under tables.
2S | Set in Order (Seiton)
2.1 | Every item has a fixed, marked place (outline, tool shadow, label or location address).
2.2 | Layout follows frequency of use: the most frequent within hand's reach, the rarer further away.
2.3 | Storage locations have a marked minimum and maximum level.
2.4 | Floor marking (zones, routes, pallet positions) is legible, and fire equipment and emergency exits are accessible.
2.5 | Racks, cabinets and containers are clearly labelled (labels understandable to a new person).
2.6 | A missing or misplaced item is visible at once (visual check within 30 seconds).
2.7 | Cables, hoses and wires are organised and neither hinder work nor create a trip hazard.
2.8 | Waste bins and sorted waste have a fixed, marked place.
3S | Shine (Seiso)
3.1 | Floors, worktops and machines are clean (no dust, chips, oil, material residue).
3.2 | The cleaning plan clearly states: what, who, how often and with what is cleaned.
3.3 | Cleaning tools and supplies are available on site, complete and in working order.
3.4 | Cleaning is combined with inspection: leaks, looseness, seepage and damage are reported.
3.5 | Sources of contamination (leaks, dust, process waste) are identified and eliminated at the source.
3.6 | Lighting works and is clean; guards, windows and information boards are legible.
3.7 | Waste bins are not overfilled and are emptied according to schedule.
3.8 | Oil and chemical zones are sealed and clean; spill trays and absorbents are available.
4S | Standardize (Seiketsu)
4.1 | The area's appearance standard (photos of the target state) is available in the area and current.
4.2 | Marking rules (colours, labels, symbols) are uniform in the area and consistent with plant rules.
4.3 | Roles and responsibilities are defined: area owner, 5S leader, people responsible for zones.
4.4 | Visual management works: markings, indicators and information boards are complete and legible.
4.5 | A daily (5-minute) 5S checklist exists and is actually filled in.
4.6 | Standards are visual (photos, drawings, colours) and understandable without reading long instructions.
4.7 | New employees are trained in the 5S standard of their area, and the training is documented.
4.8 | Changes (new machine, layout change, new product) result in an update of the 5S standard.
5S | Sustain (Shitsuke)
5.1 | Employees keep order up to date, without reminders or inspection.
5.2 | The daily 5 minutes at the end of the shift (cleaning and check) is carried out.
5.3 | Audits take place on schedule, and the results are posted in the area.
5.4 | Actions from previous audits are completed on time.
5.5 | Management regularly visits the area and checks 5S on site (gemba).
5.6 | Employees know the 5S rules and can explain what their duties are.
5.7 | Employee ideas and comments about 5S are collected and considered, and authors get feedback.
5.8 | 5S results are trended and discussed in meetings; the score holds at the target level or rises.
AUDIT RESULTS (calculated automatically)
1S Sort
2S Set in Order
3S Shine
4S Standardize
5S Sustain
OVERALL SCORE (average of 1S–5S)
Audit completeness (answers out of 40)
| (helper) audit with a score and area | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
(helper) area¦number key

## Dashboard
5S results dashboard
Enter the company or client name | [8 empty] | As of: | 2026-10-28
Area: | Production line 1 |  |  |  | ← choose an area from the list (the dashboard recalculates automatically)
LATEST SCORE |  |  | CHANGE VS PREVIOUS |  |  | TARGET |  | NUMBER OF AUDITS | ACTIONS: OPEN / OVERDUE
– |  |  | – |  |  | 80% |  | 0 | 0 / 0
no audits |  |  | no previous audit |  |  | warning threshold: 60% |  | fill in the Scores tab | in the selected area
Criterion |  | First audit | Previous | Latest | Change (pp) | To target (pp) | Score
1S Sort |  | – | – | – | – | – | –
2S Set in Order |  | – | – | – | – | – | –
3S Shine |  | – | – | – | – | – | –
4S Standardize |  | – | – | – | – | – | –
5S Sustain |  | – | – | – | – | – | –
OVERALL SCORE |  | – | – | – | – | – | –
Area ranking (latest audit of each area)
Rank | Area |  |  | Score | Audits | Score

## Action_plan
Action plan
Enter every finding from an audit, daily check or gemba here: with an owner and a deadline. The status "Closed" + a closing date drives the statistics.
Sample entry: 12.03.2026 ¦ 5S audit ¦ no. 7 ¦ Production line 1 ¦ 2S Set in Order ¦ No labels on rack R-04 ¦ Print and mount labels ¦ 5S leader ¦ 26.03.2026 ¦ Medium ¦ Closed ¦ 24.03.2026
| All entries |  | Open and in progress |  | Overdue |  | Closed | Closed on time
| 0 |  | 0 |  | 0 |  | 0 | –
Open by criterion: | 1S: 0 |  | 2S: 0 |  | 3S: 0 |  | 4S: 0 |  | 5S: 0
Lp. | Report date | Source | Audit no. | Area | Criterion | Problem description | Corrective action | Owner | Deadline | Priority | Status | Closing date | Days overdue | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
Formulas:
Days overdue = IF(OR([Deadline]="",[Status]="Closed",[Status]="Cancelled"),"",MAX(0,TODAY()-[Deadline]))

## Red_tags
Red tag register
Enter every item marked with a red tag here. Tag number = number from the printable form. A decision should be made within 7 days.
Sample entry: 05.02.2026 ¦ Production line 1 ¦ 5S leader ¦ Assembly fixture (2023 model) ¦ 3 ¦ Unneeded ¦ Move to another area ¦ Production manager ¦ 12.02.2026 ¦ Completed ¦ 11.02.2026
Tags in total |  | Pending decision | Past decision deadline |  |  | Completed |  | Average completion time (days)
0 |  | 0 | 0 |  |  | – |  | –
Tag no. | Date tagged | Area | Reported by | Item / description | Quantity | Reason | Decision | Decision owner | Decision deadline | Status | Completion date | Days open | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
Formulas:
Days open = IF(OR([Date tagged]="",[Status]="Completed"),"",TODAY()-[Date tagged])

## Audit_schedule
5S audit schedule
Block 1: enter the planned number of audits per month (yellow fields). Block 2 calculates itself from the Scores tab. Green = done, red = overdue.
Year: | 2026
Month start (helper) |  |  | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Month end (helper) |  |  | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31
BLOCK 1: PLAN (number of planned audits)
Area | Responsible auditor | Frequency | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Plan total
Production line 1 | [14 empty] | 0
Production line 2 | [14 empty] | 0
Materials warehouse | [14 empty] | 0
Finished goods warehouse | [14 empty] | 0
Tool room | [14 empty] | 0
Maintenance | [14 empty] | 0
Quality control | [14 empty] | 0
Packing | [14 empty] | 0
BLOCK 2: COMPLETION (from the Scores tab, calculated automatically)
Area | Responsible auditor | Frequency | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Plan completion (completed months)
Production line 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Production line 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Materials warehouse |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Finished goods warehouse |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tool room |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maintenance |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quality control |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Packing |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Legend: green = planned audits done, red = overdue (month has passed), blue = still ahead. An audit counts when it has a full score and a chosen area.
Formulas:
Plan total = IF([Area]="","",IF(SUMPRODUCT((D5:O5<TODAY())*D9:O9)=0,"",SUMPRODUCT((D5:O5<TODAY())*(([Jan]:[Dec]<D9:O9)*[Jan]:[Dec]+([Jan]:[Dec]>=D9:O9)*D9:O9))/SUMPRODUCT((D5:O5<TODAY())*D9:O9)))

## Rollout_90_days
5S rollout plan: 30 / 60 / 90 days
Fill in owners and dates and update the status as you go. Progress calculates itself.
Rollout progress
| Stage | Tasks | Done | Progress
| Days 1–30: foundation and pilot | 12 | 0 | 0%
| Days 31–60: standard and expansion | 8 | 0 | 0%
| Days 61–90: sustaining and rhythm | 7 | 0 | 0%
| Total | 27 | 0 | 0%
Lp. | Stage | Task | Completion criterion | Owner | Deadline | Status | Notes
1 | Days 1–30: foundation and pilot | Appoint the rollout sponsor and the 5S leader | The sponsor (plant or production manager) and the leader have their roles and time in the calendar written down. |  |  | To do
2 | Days 1–30: foundation and pilot | Choose a pilot area | One area with visible potential and an engaged shift manager. Neither the worst nor the best in the plant. |  |  | To do
3 | Days 1–30: foundation and pilot | Set goals and indicators | A written audit score target (e.g. 80%), a deadline and 2–3 measurable outcomes (search time, floor space, number of reports). |  |  | To do
4 | Days 1–30: foundation and pilot | Train the pilot team (60–90 min) | Attendance list; the team knows the 5 steps, the red tag and the quarantine zone rules. |  |  | To do
5 | Days 1–30: foundation and pilot | Take baseline photos | "Before" photos from the same spots that will later be used for the "after" photos. |  |  | To do
6 | Days 1–30: foundation and pilot | Run the zero audit | The full audit sheet in the Excel file; the result is the reference point. |  |  | To do
7 | Days 1–30: foundation and pilot | Prepare materials | Red tags, tape, labels, a board, containers for the quarantine zone, bags, cleaning supplies. |  |  | To do
8 | Days 1–30: foundation and pilot | 1S campaign: sorting with red tags | All items of unclear status tagged and entered in the register. |  |  | To do
9 | Days 1–30: foundation and pilot | Resolve the red tags | Decisions within 7 days; the quarantine zone emptied by the agreed deadline. |  |  | To do
10 | Days 1–30: foundation and pilot | 2S campaign: places, labels, outlines | Every item has an address; min/max set for materials. |  |  | To do
11 | Days 1–30: foundation and pilot | 3S campaign: cleaning and sources of dirt | The area cleaned, the three main contamination sources identified with actions assigned. |  |  | To do
12 | Days 1–30: foundation and pilot | First audit after the campaign | Audit done by someone other than the leader; result compared with the zero audit. |  |  | To do
13 | Days 31–60: standard and expansion | Write down the area standard | Target-state photos posted in the area, described, with an update date. |  |  | To do
14 | Days 31–60: standard and expansion | Introduce the daily 5-minute check | List filled in by operators at the end of the shift; a one-week test on one shift, then all shifts. |  |  | To do
15 | Days 31–60: standard and expansion | Post the 5S board in the area | A board with the score, trend, action plan and the area owner's name. |  |  | To do
16 | Days 31–60: standard and expansion | Train auditors and run calibration | At least 3 auditors; a joint audit of one area and agreed scores. |  |  | To do
17 | Days 31–60: standard and expansion | Set the audit schedule | A yearly schedule in the "Audit_schedule" tab, with auditors and dates. |  |  | To do
18 | Days 31–60: standard and expansion | Extend 1S–3S to 2–3 more areas | For each area: zero audit, 1S–3S campaign, post-campaign audit. |  |  | To do
19 | Days 31–60: standard and expansion | First cycle of cross audits | Auditors assess areas they do not run; results in the file. |  |  | To do
20 | Days 31–60: standard and expansion | First review of the action plan | All actions have an owner and a deadline; no more than 10% overdue. |  |  | To do
21 | Days 61–90: sustaining and rhythm | Start the monthly 5S review | A 30–45 minute meeting with results, trend and the oldest actions. |  |  | To do
22 | Days 61–90: sustaining and rhythm | Introduce weekly management gemba | A manager visits one area a week, asks questions and records observations. |  |  | To do
23 | Days 61–90: sustaining and rhythm | Plan auditor rotation | The same auditor does not assess the same area twice in a row. |  |  | To do
24 | Days 61–90: sustaining and rhythm | Agree a form of recognition for teams | Recognise the best area and the team with the greatest progress. No competition at the expense of rigour. |  |  | To do
25 | Days 61–90: sustaining and rhythm | Update standards after changes | Every change in the area has an entry and current photos. |  |  | To do
26 | Days 61–90: sustaining and rhythm | Summarise the 90 days | Report: results, effects, conclusions, costs; comparison with the written goals. |  |  | To do
27 | Days 61–90: sustaining and rhythm | Decide on a plant-wide rollout | Sponsor's decision with a plan for the next areas and resources. |  |  | To do

## Calculations
Helper calculations for the Dashboard panel. Do not edit.
Selected area | Production line 1
Number of audits with a score | 0
Column of the latest audit
Column of the previous audit
First audit in the trend window | 1
Column of the first audit
j | k-th audit | kolumna | etykieta | overall score | target | Note: missing values in column E are intentional (empty trend points); the chart skips them.
1 |  |  |  | #N/A | 80%
2 |  |  |  | #N/A | 80%
3 |  |  |  | #N/A | 80%
4 |  |  |  | #N/A | 80%
5 |  |  |  | #N/A | 80%
6 |  |  |  | #N/A | 80%
7 |  |  |  | #N/A | 80%
8 |  |  |  | #N/A | 80%
9 |  |  |  | #N/A | 80%
10 |  |  |  | #N/A | 80%
11 |  |  |  | #N/A | 80%
12 |  |  |  | #N/A | 80%
Criterion | First audit | Latest audit | Target
1S Sort | 0% | 0% | 80%
2S Set in Order | 0% | 0% | 80%
3S Shine | 0% | 0% | 80%
4S Standardize | 0% | 0% | 80%
5S Sustain | 0% | 0% | 80%
Area | n audits | latest col. | wynik | sort key | first col.
Production line 1 | 0
Production line 2 | 0
Materials warehouse | 0
Finished goods warehouse | 0
Tool room | 0
Maintenance | 0
Quality control | 0
Packing | 0